## Project Schedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Project Two
Enter Company Name in cell B2. | Complete this template by replacing the bracketed text with the relevant information in each row. Also, in the relevant columns, be sure to enter start and end dates and experiment with entering progress percentages to create the Gantt chart bars.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  | 2025-11-13
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  | 1 |  |  | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-11-10 to 2026-01-04
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | PROGRESS | START | END | DAYS | time axis 2025-11-10 to 2026-01-04
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Planning Phase
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Project Start Milestone |  | 2025-11-13 | 2025-11-13 | 1
| Create the official Authentication Policy |  | 2025-11-14 | 2025-11-15 | 2
| Identify and classify sensitive data |  | 2025-11-19 | 2025-11-21 | 3
| Determine security levels for each category |  | 2025-11-22 | 2025-11-24
| Initiant and develop response procedures for cyber threats |  | 2025-11-25 | 2025-11-27
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Preparation Execution Phase
| Present official NIST Cybersecurity Framework (CSF) |  | 2025-11-28 | 2025-11-30
| Hire and instruct contractors on office security upgrades |  | 2025-12-01 | 2025-12-03
| Acquire the type of 2FA and make a plan to deploy it |  | 2025-12-04 | 2025-12-06
| Update and finalize security documentation |  | 2025-12-07 | 2025-12-09
| Planning and Preparation Complete Milestone |  | 2025-12-10 | 2025-12-10 | 1
Execution Phase
| Enforce new password and authentication policies |  | 2025-12-11 | 2025-12-15 | 5
| Deploy and verify two-factor authentication (2FA) |  | 2025-12-15 | 2025-12-18 | 4
| Implement access control lists (ACLs) and VLAN configurations |  | 2025-12-19 | 2025-12-21
| Monitor network traffic and verify control effectiveness |  | 2025-12-22 | 2025-12-22 | 1
Finalization Phase
| Review implemented controls and conduct system audit |  | 2025-12-24 | 2025-12-26
| Ensure all employees understand and use 2FA correctly |  | 2025-12-26 | 2025-12-27
| Documenting lessons learned and finalize reports |  | 2025-12-28 | 2025-12-28
| Deliver final project results and closeout |  | 2025-12-29 | 2025-12-29 | 1
Adapted from a template by TeamGantt (2019), https://www.teamgantt.com/

## Resource Allocation
Complete this template by entering the relevant information in each row.
Task | Resource | Rationale
Project scope and objectives | Project Manager (me) | I will be handling this part, as it’s my duty to plan the project, set goals, and ensure the timeline aligns with stakeholders' expectations.
Creating the offical Authentication Policy | Software Engineers | The software engineers are responsible for setting up and securing the authentication policy and making sure it’s applied correctly.
Identify and classify sensitive data | Project Manager (me) & Software Engineers | As a project manager, I’ll work with the software team to determine which data is most sensitive and requires the highest level of protection.
Determining security levels for each data category | Software Engineers | The software engineers will determine which access levels and permissions apply to each type of data category.
Initiant and develop response procedures for cyber threats | Project Manager (me) & Hardware Engineers | I will coordinate the plan, while the hardware engineers ensure systems and devices are ready for any threat response.
Present NIST Cybersecurity Framework (CSF) | Project Manager (me) | I will explain the NIST CSF to everyone involved so the whole team understands what standards we’re following correctly.
Hire and instruct contractors on office security upgrades | Contractor & Project Manager (me) | Contractors will handle the physical security work, and I’ll make sure everything is done on time and correctly.
Acquire the type of 2FA and make a plan to deploy it | Software Engineers | Software engineers will test and set up the 2FA system to make sure it works and runs smoothly with existing accounts.
Update and finalize security documentation | Project Manager (me) | I will further document everything so the project has a clear record of what was done and what needs to be maintained.
Enforce new password and authentication policies | Software Engineers | Software engineers will roll out the new password rules and update systems for better security standards.
Deploy and verify two-factor authentication (2FA) | Software Engineers & Project Manager (me) | The software engineers will set it up, and I’ll verify that it’s working correctly for all users.
Implement access control lists (ACLs) and VLAN configurations | Hardware Engineers | The hardware engineers handle network segmentation and access controls to securely separate departments.
Monitor network traffic and verify control effectiveness | Hardware & Software Engineers | Hardware and software engineers will check network traffic and test that all new security controls are working as intended.
Review implemented controls and conduct system audit | Project Manager (me) & Software Engineers | I will go through everything with the software team to confirm all security measures are correctly in place and working.
Ensure all employees understand and use 2FA correctly | Project Manager (me) | It is my duty and responsibility to train employees while stakeholders help reinforce the new security practices.
Documenting lessons learned and finalize reports | Project Manager (me) | I will wrap up the project by summarizing what worked well and what could be improved next time.
Deliver final project results and closeout | Project Manager (me) | My duty is to hand everything off to the stakeholders and officially close the project.