## Project Schedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Project Two
Enter Company Name in cell B2. | Complete this template by replacing the bracketed text with the relevant information in each row. Also, in the relevant columns, be sure to enter start and end dates and experiment with entering progress percentages to create the Gantt chart bars.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  | 2025-12-11
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  | 1 |  |  | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-12-08 to 2026-02-01
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | PROGRESS | START | END | DAYS | time axis 2025-12-08 to 2026-02-01
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Planning Phase
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Project Start Milestone |  | 2025-12-08 | 2025-12-08 | 1
| Create the official Authentication Policy |  | 2025-12-08 | 2025-12-10 | 3
| Determine security levels for each category |  | 2025-12-10 | 2025-12-12
| Identify and classify sensitive data |  | 2025-12-12 | 2025-12-15
| Initiant and develop response procedures for cyber threats |  | 2025-12-15 | 2025-12-20
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Prepartion Execution Phase
| Present official NIST Cybersecurity Framework (CSF) |  | 2025-12-22 | 2025-12-23 | 2
| Hire and instruct contractors on office security upgrades |  | 2025-12-23 | 2025-12-30
| Acquire the type of 2FA and make a plan to deploy it |  | 2025-12-30 | 2026-01-09
| Update and finalize security documentation |  | 2026-01-05 | 2026-01-09
| Forward the official Authentication Policy |  | 2026-01-09 | 2026-01-10 | 2
Execution Phase
| Enforce new password and authentication policies |  | 2026-01-12 | 2026-01-16 | 5
| Deploy and verify two-factor authentication (2FA) |  | 2026-01-16 | 2026-01-23 | 8
| Implement switches, access control lists (ACLs) and VLAN configurations |  | 2026-01-23 | 2026-02-06
| Monitor network traffic and verify control effectiveness |  | 2026-02-06 | 2026-02-13
| Install and configure PDF conversion feature |  | 2026-02-15 | 2026-02-20
| Test PDF export and confirm functionality |  | 2026-02-20 | 2026-02-24 | 5
Finalization Phase
| Review implemented controls and conduct system audit monitoring |  | 2026-02-24 | 2026-02-24
| Ensure all employees understand and use 2FA correctly |  | 2026-02-28 | 2026-03-03
| Confirm passwords are set for the new Authentication Policy |  | 2026-03-03 | 2026-03-05
| Documenting lessons learned and finalize reports |  | 2026-03-05 | 2026-03-10
| Deliver final project results and closeout |  | 2026-03-10 | 2026-03-12
Adapted from a template by TeamGantt (2019), https://www.teamgantt.com/

## Resource Allocation
Complete this template by entering the relevant information in each row.
Task | Resource | Rationale
Create the official Authentication Policy | Project Manager | The project manager oversees policy development and ensures it aligns with project goals.
Determine security levels for each category | Software engineers | They must understand system access needs and can define proper security levels.
Identify and classify sensitive data | Software engineers | They work directly with systems and know where sensitive data exists.
Initiant and develop response procedures for cyber threats | Software engineers | They help build realistic and effective response procedures based on technical flow.
Present official NIST Cybersecurity Framework (CSF) | Project Manager | The project manager communicates project direction and security framework requirements.
Hire and instruct contractors on office security upgrades | Hardware Engineers team lead | They oversee technical work and ensure contractors comply with ACME’s security requirements.
Acquire the type of 2FA and make a plan to deploy it | Hardware and Software Engineers | They evaluate compatibility and plan deployment for the organization.
Update and finalize security documentation | Project Manager | The project manager documents project policies, updates, and changes.
Forward the official Authentication Policy | Project Manager | Project manager is responsible for communicating approved policies to the team and stakeholders.
Enforce new password and authentication policies | Project Manager | Project manager ensures that all departments follow the updated authentication standards.
Deploy and verify two-factor authentication (2FA) | Software engineers | They have the expertise to configure, test, and confirm 2FA functionality.
Implement switches, access control lists (ACLs) and VLAN configurations | Hardware Engineers | They are qualified to replace hardware and configure secure network segmentation.
Monitor network traffic and verify control effectiveness | Software engineers | They use monitoring tools to verify that segmentation and ACLs are working correctly.
Install and configure PDF conversion feature | Contractors | They understand document conversion and software setup
Test PDF export and confirm functionality | Software Engineers + DBA | They verify the tool works with ACME's reporting system.
Review implemented controls and conduct system audit monitoring | Project Manager + Software Engineers | Both ensure controls work as intended, and audit logs are appropriately captured.
Ensure all employees understand and use 2FA correctly | Project Manager | They oversee training follow-up and user compliance.
Confirm passwords are set for the new Authentication Policy | Software engineers | They can verify account changes and enforce the updated policy.
Documenting lessons learned and finalize reports | Project Manager | The project manager completes the final reports and summarizes project takeaways.
Deliver final project results and closeout | Project Manager | The project manager is responsible for final review, approval, and project completion.